## Slide 1
THE 12TH STEERING COMMITTEE MEETING OF THE ASEAN-AVRDC REGIONAL NETWORK FOR VEGETABLE RESEARCH AND DEVELOPMENT (AARNET)
23 to 25 May 2017
World Vegetable Center, Shanhua,Tainan, Taiwan

## Slide 2
Matter arising | Actions to be taken | Action by | Timeline | Status
AARNET Secretariat updated and highlighted draft Strategic Plan of Action (SPA) prepared by ASWGC for the Action Programmes 1.3 and 1.7, for the Meeting’s consideration particularly with regard to the output indicators to be set. | AARNET Secretariat to circulate the SPA to AMS for their input on output indicators. | AARNET Sec | By June 2017 | Draft SPA was sent to AMS for input on output indicators on 19 May 2016. No response from AMS except from Myanmar showed agreeable on the draft SPA.
Follow-up:

## Slide 3
1.3 Develop yield and productivity enhancing technologies and best practices that involve land use intensification in a sustainable manner, bearing in mind that expansion of cultivable land rapidly reaches its limits even in the land-abundant AMS. | 1.3.1 Promote sustainable and optimisation of utilisation of land and natural resources and agricultural innovation on improving productivity and sustainable agricultural production | 1.3.1.1 ASEAN–AVRDC Regional Network for Vegetable Research and Development (AARNET). | ASWGC/ AARNET | 2016 - 2020 | Number of technology developed
ACTION PROGRAMMES | ACTIVITIES | SUB-ACTIVITIES | RESPONSIBLE ASEAN BODIES/ LEAD COUNTRY | TIMELINE | OUTPUT INDICATORS
STRATEGIC PLAN OF ACTION (SPA) FOR THE ASEAN COOPERATION IN CROPS (2016-2020)[1]
SECTOR : AGRICULTURE
SUB-SECTOR: CROPS
WORKING GROUP: ASEAN SECTORAL WORKING GROUP ON CROPS (ASWGC)
STRATEGIC THRUST 1 : ENHANCE QUANTITY AND QUALITY OF PRODUCTION WITH SUSTAINABLE, ‘GREEN’ TECHNOLOGIES, RESOURCE MANAGEMENT SYSTEMS, AND MINIMISE PRE- AND POST-HARVEST LOSSES AND WASTE
[1] Capacity building is subsumed under activities/sub-activities in each AP

## Slide 4
ACTION PROGRAMMES | ACTIVITIES | SUB-ACTIVITIES | RESPONSIBLE ASEAN BODIES/ LEAD COUNTRY | TIMELINE | OUTPUT INDICATORS
1.7 Identify and document technology, success stories and explore new methods of extension including enhanced use of information and communications technology (ICT) and other communication facilities for dissemination of successful technologies and management systems throughout AMS | 1.7.1 Establish a successful technologies and management systems and to establish platforms to disseminate this information throughout AMSs. (Ref. AIFS ST4 A 4.1) | Develop, consolidate or strengthen websites related to crops sub-sector AARNET website | ASWGC/ AARNET ASWGC/ ASAS Project ASWGC | 2016-2020 2017 2016 - 2020 | Number of visitors to visit ASAS/APHNET website on monthly basis. % of repeat users each month A Regional Database on bio-input and regulatory database is extended to include bio-fertiliser and etc., and mechanism for its sustainability is established) Number of exchange missions conducted.