## Slide 1
Tomato
Brinjal
Cabbage
Cauliflower
Pumpkin
Black gram
Lentil
Pea
Vegetables and Pulses under WorldVeg in APART

## Slide 2: Part B: Promoting the adoption of climate resilient good agricultural practices
  B1: Climate resilient production demonstrations
  .

## Slide 3: Part B: Promoting the adoption of climate resilient good agricultural practices B1: Climate resilient production demonstrations
Direct engagement in 20% demonstrations
Need-based technical support in 80% demonstrations
100% demonstrations = 451 in 2018-19 and 914 in 2019-20
All demonstrations organized by implementing partners.
Technical support by WorldVeg

## Slide 4
Part B: Promoting the adoption of climate resilient good agricultural practices B1: Climate resilient production demonstrations
Physical Progress of Vegetable and Pulse Value Chain under OPIU(Horti) & OPIU(AGRI)
Demonstration on Climate Resilient Technology and Market Led | 2018-19 |  |  |  | 2019-20 |  | 2020-21 |  | Cumulative | 
 | Plan | Achievement |  | Total | Plan | Achieved | Plan | Achieved | Plan | Achievement
 |  | ATMA- District | WorldVeg |  |  |  |  |  |  | 
Tomato | 150 | 143 | 7 | 150 | 126 | 126 | 189 | 36 (early-ongoing) | 465 | 276
Cabbage | 150 | 139 | 11 | 150 | 112 | 112 | 168 | 80 (early-ongoing) | 430 | 262
Cauliflower | 150 | 140 | 10 | 150 | 96 | 96 | 144 | 57 (early-ongoing) | 390 | 246
Brinjal | 150 | 139 | 11 | 150 | 108 | 108 | 162 |  | 420 | 258
Pumpkin | 150 | 139 | 11 | 150 | 112 | 112 | 168 |  | 430 | 262
Black gram | 80 | 64 | 0 | 64 | 160 | 160 | 240 | Final decision from ARIASS is pending |  | 
Lentil | 50 | 40 | 10 | 50 | 100 | 100 | 150 |  |  | 
Pea | 50 | 40 | 10 | 50 | 100 | 100 | 150 |  |  | 
Pea | 50 | 40 | 10 | 50 | 100 | 100 | 150 |  |  | 

## Slide 5
Part B: Promoting the adoption of climate resilient good agricultural practices B1: Climate resilient production demonstrations
Climate resilient demonstrations | Average Yield (q/ha) (2018-2019) |  |  | Average Yield (q/ha) (2019- 2020) |  | 
 | Demo | Control | Percentage increase (%) | Demo | Control | Percentage increase (%)
Brinjal | 157 | 107 | 46 | 293 | 232 | 27.40
Cabbage | 616 | 566 | 9 | 283 | 224 | 26.34
Cauliflower | 422 | 403 | 5 | 255 | 210 | 21.43
Pumpkin | 178 | 166 | 7 | 248 | 192 | 29.16
Tomato | 181 | 141 | 29 | 324 | 275 | 17.81
Black gram | WorldVeg missed the black gram season since the project started in Nov. 2018 |  |  | 8.2 | 5.3 | 54.7
Lentil | 15 | 12 | 25 | 18.5 | 15.5 | 19.35
Pea | 63 | 51 | 23 | 66 | 53 | 24.5
Average comparative yield of demonstration vs control plot

## Slide 6: Technologies introduced & promoted by WorldVeg
Increase sustainability and climate resilience
Training to extension agents and farmers
Aim to: produce healthy, disease free seedlings with good root system; intensify cropping; reduce synthetic agro-chemical use and dependence; create safer conditions for farmers, consumers and environment.
Seedling trays
Potting mixture
Enriched vermicompost
Transplanting media
Microbial bio-fertilizers
Microbial bio-control agents
Localized fertilizer application
Intercropping
Mulching
Line sowing in pulses
Rhizobia inoculation in pulses
Sticky traps
Pheromone traps
Trap crops
Border crops
Safer alternatives to conventional synthetic pesticides
Reduced rates of agro-chemicals in demonstrations
Micronutrients
Personal protection equipment (PPE) for farmers
Awareness on pesticide handling and application

## Slide 7: Seedling tray
Healthier than seedlings from raised beds
Eliminates root damage
Minimize transplanting shock and risk of disease incidence
Cuts down on seed requirement
Easy to transport
Technologies introduced & promoted by WorldVeg

## Slide 8: Soil-less Potting mixture
3x coco-peat + 1x vermicompost + 1x charred rice husk
Plus microbial bio-fertilizers and bio-control agents
Well-matured vermicompost to be used
Soilless media
Lower risk of soil-borne diseases
Technologies introduced & promoted by WorldVeg

## Slide 9: Enriched vermicompost
Enriched using various microbial bio-fertilizers and bio-control agents
Incubated for 2 – 3 weeks following inoculation
Improves soil health
Technologies introduced & promoted by WorldVeg

## Slide 10: Transplanting media
Promotes localized application of manure/compost/fertilizer
Enriched vermicompost + farmyard manure + reduced quantities of synthetic fertilizers
Applied into transplanting pits or planting furrows.
Increases nutrient availability and improves soil health
Technologies introduced & promoted by WorldVeg

## Slide 11: Microbial bio-fertilizers and bio-control agents
Bio-fertilizers:
Azotobacter
Azospirillum
Rhizobium
Phosphorus solubilizing bacteria (PSB)
Bio-control agents:
Trichoderma
Pseudomonas
Beauveria
Metarhizium
Increases nutrient availability, soil fertility, and lowers pest damage
Technologies introduced & promoted by WorldVeg

## Slide 12: Source of procurement of bio fertilizers and bio agents
District | Vendor detail
Nagaon | Balark Biotech, B. M. Road, Amolapatty, Nagaon
Morigaon | Nazrul Islam, Krishi Vikas Kendra, Burbondha, Morigaon
Kokrajhar | National Seed Nursery, Boro Bazar Road, Kokrajhar
Kamrup | S H Enterprise, Barpeta Road, Assam 781315
Nalbari | Maa Trading, L N B Road, Nalbari
Sivasagar | Haque Beej Bhandhar, Central Market, Sivasagar
Jorhat | Surabhi Agro Service, Demow
Sonitpur | Sonitpur Nursery, Chawk Bazaar, Tezpur
Cachar | Seed House, Opp. Silchar Court, Cachar
Lakhimpur | Assam Beej Bhandar, Bazaarpati Road, North Lakhimpur
Barpeta | Kohinor Beej Bhandar, Barpeta Road, Barpeta
Golaghat | Vishal Organics and Research Centre, Jorhat
Goalpara | Goalpara Seed House, Opp. Canara Bank, Near ASTC, Goalapara
Darrang | Ahmed Agro Care, Dhula/ Rahman Agro Agency, Kkarupetia, Darrang

## Slide 13: Localized fertilizer application
Instead of broadcasting over entire field area
Localized application to root zone of individual plants
Through transplanting media
Increases fertilizer use efficiency and soil fertility
Reduces fertilizer requirement
Technologies introduced & promoted by WorldVeg

## Slide 14: Line sowing in pulses
Reduces seed requirement
Facilitates inter-cultural operations
Weeding
Balanced competition among crop plants
Less disease/ insect pest incidence
Line sowing/planting in lentil [left], compared with broadcasting [right]
Technologies introduced & promoted by WorldVeg
Line sowing in pea
Line sowing in black gram

## Slide 15: Intercropping
With quick-growing, short-duration cash crop
Increases returns
Reduces risk
Intensifies cropping
Use time required for ground-cover by cash crop
Increases resource utilization/biomass production
Amaranth in brinjal, cabbage and tomato; coriander in cauliflower; beans in pumpkin
Technologies introduced & promoted by WorldVeg
Beans as intercrop in pumpkin
Amaranth as an intercrop with cabbage

## Slide 16: Mulching
Covering soil surface with rice straw, arecanut husk, etc.
Locally available, biodegradable
Use of residue considered waste/burden in many areas
Increases soil organic matter, soil microbial populations
Conserves soil and soil moisture
Use of rice straw as mulch in tomato
Technologies introduced & promoted by WorldVeg
Use of Arecanut husk (left) and rice straw (right) as mulch in cauliflower

## Slide 17: Staking in tomato
Keeps plants erect
Prevents contact of fruits with soil
Increases air circulation
Reduces disease incidence
Improves fruit quality
Makes intercultural operation easier
Technologies introduced & promoted by WorldVeg

## Slide 18: Sticky traps
Yellow and blue
Different insect pests attracted to different colors
  e.g., whitefly to yellow
  Thrips to blue
Traps on to adhesive surface
Technologies introduced & promoted by WorldVeg
Yellow sticky trap
Blue sticky trap

## Slide 19: Pheromone traps
Attract target insects using species-specific lures and traps them
Fruit and shoot borer lures in brinjal
Spodo lures for Spodoptera in cabbage and cauliflower
Lures for fruitfly in pumpkin
Heli lures for Helicoverpa in tomato, black gram, lentil and pea
Technologies introduced & promoted by WorldVeg

## Slide 20: Trap crops
Crop-specific plant species
Attract insect pests
Keep them away from main crop
Pesticide application on trap crop if needed
Keep main crop safe from pesticide residues
Mustard in cabbage and cauliflower
African marigold in pumpkin, tomato, black gram, lentil and pea
Technologies introduced & promoted by WorldVeg

## Slide 21: Border crops
Quick-growing, tall, dense plants
Planted along field boundary
Physical deterrent to entry of insect pests
Maize for all crops
Technologies introduced & promoted by WorldVeg
Maize as a border crop in pumpkin (top) & cauliflower (below)

## Slide 22
Safer alternatives to conventional pesticides
Reduced rates of agro-chemicals
In demonstrations
Reduced quantities of fertilizers
Reduced budget for conventional pesticides
To create awareness
Facilitate use of IPM components
Neem oil
Salts of fatty acids (e.g., Lastraw®)
Foliar applications of Beauveria and Metarhizium
Technologies introduced & promoted by WorldVeg

## Slide 23: Personal protection equipment for farmers
Awareness on use of safety gear
During pesticide handling and application
Reduce health risks to farmers
Gloves
Nose masks
Safety goggles [eyewear]
Gum boots
Technologies introduced & promoted by WorldVeg

## Slide 24: Economic analysis of the demonstration (Cost: Benefit)
Crops | Demonstration cost |  | Assessment on 2019-20 demos (Rs) |  |  |  | 
 | (Veg: 0.15 ha & Pulse: 0.25ha) |  |  |  |  |  | 
 | Demo (Rs.) | For 1 ha (Rs.) | Demo area (ha) | Average yield per ha (t/ha) | Market price per ton (Rs.) | Total income per ha (Rs.) | Cost: Benefit
Brinjal | 12,284 | 81,893 | 16.2 | 29 | 15,000 | 435000 | 5.3
Cabbage | 13,240 | 88,266 | 16.8 | 28 | 13,000 | 364000 | 4.1
Cauliflower | 13,080 | 87,200 | 14.4 | 25 | 15,000 | 375000 | 4.3
Pumpkin | 16,326 | 1,08,840 | 16.8 | 25 | 18,000 | 450000 | 4.1
Tomato | 12,060 | 80,400 | 18.9 | 32 | 13,000 | 416000 | 5.2
Black gram | 7,353 | 29,412 | 40 | 0.85 | 80,000 | 68,000 | 2.31
Lentil | 7,518 | 30,072 | 25 | 1.50 | 80,000 | 120,000 | 4.00
Pea | 8,360 | 33,440 | 25 | 5.00 | 55,000 | 275,000 | 8.22

## Slide 25
Year | Target group | Training topic | No. of training | Total participants | Male | Female
2018-19 | Farmers | Package of Practices on five vegetables and pulses | 66 | 1814 | 1444 | 370
2019-20 | ATMA officials | Improved Production Guides(IPGs) of vegetables & pulses | 17 | 281 | 232 | 49
 | Farmers | 1st Phase Training on IPGs | 111 | 3244 | 2658 | 586
 | Farmers | 2nd phase traing on IPGs | 31 | 737 | 546 | 191
Total |  |  | 225 | 6076 | 4880 | 1196
Technical training on climate resilient and IPM technologies in vegetable and pulses

## Slide 26
Technical training to farmers at different stages by WorldVeg team

## Slide 27
Technical training to district team by WorldVeg at different districts

## Slide 28: Workshop conducted in 2019-2020 as a part of AWP
Workshops with AAU
Identification and prioritization of best performing varieties of vegetables and pulses:
The objective of these workshops was to discuss, in a forum of farmers (29), traders (2), scientists (34) and implementing partners (32), suitable vegetable and pulse crop varieties to be used in demonstration plot in each of the 15 APART districts. Selected varieties were popular and desired varieties in each district
2 workshops were conducted at:
  Guwahati on 9th July 2019 with a total of 47 numbers of participants
  Jorhat on 11th July 2019 with a total of 40 numbers of participants
Two virtual workshops:
  Validation of IPM package of vegetables and pulses on 22nd June 2020
  Drafting of crop manuals on vegetables and pulses on 23rd June 2020

## Slide 29: Identification and prioritization of best performing varieties of vegetables and pulses crops for 2019-2020 WorldVeg demonstration
Workshop at Guwahati
Workshop at Jorhat
Crop | Variety used during 2019-20
Brinjal | Navkiran, Pusa Purple Long, VNR-212, Sungro 33, Local Black, BSS 793, Bharat 436
Cabbage | Wonderball, Rareball, BC-76, Green Express, Pragati Plus
Cauliflower | White Excel, Madhuri, Megha, Mahi, Aanchal, NS-95, Cashmere, Snow heart
Pumpkin | Arjuna, Madhu
Crop | Variety used during 2019-20
Tomato | INDAM 1006, Hard Rock, US 440, Rocky, Trishul, Anup
Black gram | IPU-02-43
Lentil | WBL 77
Pea | Kashi Nandini

## Slide 30
Workshops with DOH&FP
Rapid Assessment of Training needs
  The objective of this workshop was to collect and assess the requirements and expectations of stakeholders from the Project. District nodal officers of APART, ATMA officials, District Horticulture Coordinators and progressive farmers attended the workshop
  2 workshops conducted at:
  Guwahati on 5th August 2019 with a total of 54 participants from 8 districts (Cachar, Goalpara, Kamrup, Barpeta, Kokrajhar, Nalbari, Darrang, Dhubri)
  Sonitpur on 7th August 2019 with a total of 88 participants from 7 districts (Morigaon, Lakhimpur, Nagaon, Jorhat, Sivasagar, Sonitpur, Golaghat)
  A report was prepared based on the outcome of this workshop, which was shared with ARIASS and DOH&FP
Workshop conducted in 2019-2020 as a part of AWP

## Slide 31: Rapid Assessment of Training Needs- 2019-2020
Group discussion and presentation by team during the workshop at Guwahati
Group discussion and presentation by team during the workshop at Sonitpur
Team Cachar
Team Goalpara
Team Nagaon
WorldVeg team addressing the participants

## Slide 32
Workshops with DOH&FP
Training of Trainers (ToT)
  The objective of ToT is to train DHCs and ATMA master trainers on WorldVeg strategies and approaches to the 2019-20 demonstrations. Multiple sessions on various vegetable and pulse production topics were covered
  2 workshops of three days each were conducted at:
  Jorhat from 21st August to 23rd August 2019 with a total of 35 participants
  Guwahati from 26th August to 28th August 2019 with a total of 43 participants
Workshop conducted in 2019-2020 as a part of AWP

## Slide 33: Training of trainers (2019-2020)
3 days Training of Trainers (ToT) at Jorhat
3 days Training of Trainers (ToT) at Guwahati

## Slide 34: Crop manuals & Improved Production Guides (IPGs)
For 8 crops
Detailed instructions + tips
Crop production aspects + WorldVeg interventions
Nursery through harvest
Easy-to-use, comprehensive
Farmers + extension agents
Training materials prepared by WorldVeg team

## Slide 35
Farmers’ friendly crop manuals and IPGs on 8 crops are shared with ARIASS and AAU and DoH&FP. WorldVeg shared the English versions of the crop manuals and IPGs to implementing partners for translation to local languages and distribution at district and farmers’ level
Training materials prepared by WorldVeg team

## Slide 36: Leaflets
On specific topics
2-page hand-outs
Leaflets prepared under APART by WorldVeg are shared with implementing partners for translation and distribution.
Training materials prepared by WorldVeg team

## Slide 37: Field activity videos
Three videos for technical training both in English and Assamese prepared and shared with implementing partners
  How to prepare potting mixture and sowing in seedling trays
  How to prepare transplanting media
  Field preparation for transplanting
Farmers testimonial video with English subtitle
Training videos prepared by WorldVeg team

## Slide 38
Activities planned under AWP 2020-21

## Slide 39
Part B: Promoting the adoption of climate resilient good agricultural practices B1: Climate resilient production demonstrations
Activities planned under AWP 2020-21: DoH&FP
Crops | Number of demonstration | Remark
Brinjal | 162 | Input distribution, technical training and sowing of seeds in seedling trays has been initiated. Few demonstrations are planned to conduct in the late season (Feb, 2020)
Cabbage | 168 | Early season cabbage and cauliflower demonstration are conducted in six districts with an aim to get good market price
Cauliflower | 144 | 
Pumpkin | 168 | The demonstration initiated in Nov. 2020 after rice harvest. Technical training of farmers are on going at village level
Tomato | 189 | The demonstration initiated in Nov. 2020 after rice harvest. Technical training of farmers are on going at village level
Total | 831 | 20% of the demonstration will be followed by rice or other crop to facilitate cropping sequence

## Slide 40: Production of WorldVeg OP seeds of tomato and pumpkin under AWP 2020-21- a new activity with DoH&FP
Production of seeds of WorldVeg open pollinated (OP) lines of tomato and pumpkin through seed village will be carried out in pilot basis with an objective that farmers can be benefited from the introduction of open pollinated vegetable varieties with characteristics similar to hybrid varieties and overcome the associated problems of hybrid varieties such as:
  Hybrid seeds are very expensive compared to open pollinated seed
  Farmers have to buy fresh hybrid seeds for every planting season
  Fake hybrid seeds are on the increase
A strategy paper has been prepared by WorldVeg and shared with DoH&FP
Selection of OP line for seed production:
  Tomato: AVTO 1424
  Pumpkin: AVPU 1391
    Seeds have been dispatched from WorldVeg-South Asia
District selected for production of OP seeds:
  Tomato: Pabhoi Greens, Biswanath under DoA Sonitpur and KVK, Khumtai, Golaghat
  Pumpkin: DAO, Jorhat and KVK Nalbari

## Slide 41
Thank you